## Slide 1: Milestone 2
WE99: West-East Team
Sean Sinnott
Mark Ford
Alexander Zaman
Tim Stefanski
Alan Orcharton
Harvard Extension School
CSCIE-99: Final Project
Biomedical Plate, Assay, and Results Management System

## Slide 2: WE99 Team Vision
The team focus is providing outstanding tools to assist in analyzing the dose response characteristics potential drugs.
We will provide beautiful interactive visualization tools that will assist the scientist in:
Creating and managing experimental plate sets for dose response experiments
Performing quality control checks on plate results and plate controls
Performing Interactive analysis of dose response results.
The team will store the experimental results and the analysis of the results so that the historic experimental analysis can be reviewed or reproduced at any time.
Scientists will be able to save the results for further analysis or publish their analysis, making it available to all other users.

## Slide 3: Presentation Outline
Overview of Presentation
Project Status
System Design – ??
System Demo – ??
Testing – ??
Risks - ??

## Slide 4: Project Status
The We99 team is using some Agile development methods and planning practices. Progress of the project is measured in terms of the number of stories and number of story points that are delivered.
We will review project status based on:
Burn Up and Team Velocity
Projected Completion base on Velocity
Key Functionality Goals Estimated form Milestone 1
Demonstration of Functionality

## Slide 5: Project Status
Chart: We99 Burn-up Chart
| 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0
Project Total Points | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
Cumulative Completed | 0 | 36 | 66 | 76 | 129 | 154 | #N/A | #N/A | #N/A | #N/A | #N/A
Estimated Trajectory | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 360

## Slide 6: Project Status – Team Velocity
Average points / Iteration = 30.8
Team Velocity = 30.8 points / iteration

## Slide 7: Project Status - Projection
Based on Projected Velocity Team is predicted to complete 304 / 360 points

## Slide 8: Project Status – Milestone 2 Predictions
Predicted Deliverable | Status
Domain Model | Initial Version Complete
Web Service Interfaces | Initial Version Complete
Plate Map Editor | In Progress
Web Services for Plate Editor | Initial Version Complete
Web Services for Heat Maps | Initial Version Complete
Heat Maps | Initial Version Complete
Experiments Page | Initial Version Complete

## Slide 9
Application Demonstration

## Slide 10
Design - Web Service Interfaces

## Slide 11
Design – Domain Model

## Slide 12: Project Risks
Risks
  Delivering Complete Functionality based on velocity
    “Learning” does not count as points – velocity should increase
    Cut some “Special Feature” Scope
  Integration with other teams
    Design meetings with other teams planned
  Stories take longer that estimated
    Keep a burn-up chart and prioritize stories
  Getting of Good Test Data
    Professor and TA may be able to get more